Software Project Management Plan

CULTURATI

Team 22

Ayesha Nizam, 22001260

Göktuğ Şenkoyun, 22103191

Talal Salman Zafeer, 22001483

Tarık Ebubekir Koca, 22103032

Enes Memigüven, 22002674

Bilkent University

Department of Information Systems and Technologies

08.01.2025

- Change History

| File Name | Document Type | Deliverable | Version | Submission Date |
| --- | --- | --- | --- | --- |
| Team22_SPMP_FR1 | MS Word 2013 | 3 | 1 | 04.12.2024 |
| Team22_SPMP_FR2 | MS Word 2013 | 3 | 2 | 08.01.2025 |

- Change List

The following changes were made to Software Project Management Plan version 1:

- The Executive Summary was updated with new values for effort estimations and cost estimation.

- Cash flow diagram, Cost Estimation, Net Present Value has been updated.

- Project Schedule changed. More detail added to the last milestones.

- Project Estimation was updated by recalculating effort estimation.

- In Project Monitoring and Measuring any unnecessary activities have been removed.

- Project Scope updated based on all the new changes on the document.

- In Product Verification and Validation any extra tests and verification that we will not perform has been removed.

- Project Team

| Name, Surname | Student Id Number | e-mail |
| --- | --- | --- |
| Ayesha Nizam | 22001260 | ayesha.nizam@ug.bilkent.edu.tr |
| Göktuğ Şenkoyun | 22103191 | goktug.senkoyun@ug.bilkent.edu.tr |
| Talal Salman Zafeer | 22001483 | talalsalmanzafeer@gmail.com |
| Tarık Ebubekir Koca | 22103032 | tebubekirkoca03@gmail.com |
| Enes Memigüven | 22002674 | enes54657@gmail.com |

- Project Details

| Project Name | CULTURATI |
| --- | --- |
| Software Name | CULTURATI |
| Company Name | Horizon Europe RIA |
| Academic Advisor | Neşe Şahin Özçelik |
| Github URL | https://github.com/AyeshaNizam-5/CULTURATI |
| WEB page |  |

- Individual Contributions Overview

| Name, Surname | Summary of Contributions to the SPMP Document |
| --- | --- |
| Ayesha Nizam | Responsible for Work packages and Dependencies, Agile Estimation, discussion, Executive Summary, Scope, document formatting. Made changes according to feedback. |
| Göktuğ Şenkoyun | Responsible for Work packages and Dependencies, Use Case Based estimation, Discussions, Minor formatting. |
| Talal Salman Zafeer | Responsible for Product Verification and Validation, Software Development Environment |
| Tarık Ebubekir Koca | Responsible for Cost Estimation, Net Present Value, Budget and Resource Allocation. |
| Enes Memigüven | Responsible for the project monitoring and measuring part |

### Executive Summary

This Software Project Management Plan (SPMP) provides a detailed roadmap for the successful development of the CULTURATI Content Management System (CMS), including key activities, resource allocation, effort estimations, and monitoring strategies. The project schedule consists of Work Packages (WPs), 9 milestones, and 4 deliverables, of which the Initial Plan, Software Requirements Specification (SRS), and SPMP, SDD and 1st increment have been completed. Resource requirements include personnel, hardware, and software, with 5 team members actively contributing, supported by tools such as GitHub for version control, AWS for cloud services, and project management platforms to ensure smooth execution. The total cost estimation, calculated using Net Present Value (NPV) amounts to 10.160 TL and 360.00 USD .For project effort estimation, three techniques were applied: Work Breakdown Structure (WBS)-based estimation resulted in 506 person-hours and is considered the most accurate due to its detailed task decomposition. Use case based effort estimation gave 3020 person hour as effort and agile estimation gave Project monitoring and measuring will involve weekly Scrum-based meetings and metrics such as task completion rates, defect density, and project timelines, stored systematically to track progress and quality. Product verification and validation include functional testing, and integration testing, with prepared sample test cases ensuring the system meets functional and non-functional requirements while focusing on reliability and user satisfaction. The software development environment comprises React.js, Node.js, PostgreSQL, and AWS cloud services, with tools like Visual Studio Code (IDE), Postman (API testing), and GitHub enabling streamlined development, testing, and deployment. In conclusion, this SPMP ensures the CULTURATI CMS project follows a structured, realistic, and well-monitored path with accurate effort estimations, robust resource allocation, and comprehensive validation strategies, aligning all project deliverables to meet stakeholder expectations within the defined timeline.

### Table of Contents

Page Number

Executive Summary	i

1	Scope	1

2	Project Schedule	3

2.1	Work Packages & Dependencies	3

2.2	Resource Requirements	20

2.3	Cost Estimation, Net Present Value, Budget and Resource Allocation	22

3	Project Effort Estimation	24

3.1	Work Breakdown Structure (WBS) - Decomposition-Based Estimation	24

3.2	Use Case Based Estimation	24

3.3	Agile Estimation	36

3.4	Discussion	43

4	Project Monitoring and Measuring	46

4.1	Monitoring Progress	46

4.2	Metrics	46

4.2.1	Project Metrics	46

4.2.2	Product Metrics	46

4.2.3	Process Metrics	47

4.3	Purpose of Collecting Metrics	47

5	Product Verification and Validation	48

5.1	5.1 Plan	48

5.1.1	Objectives	48

5.1.2	Approach	48

5.2	Verification and Validation Techniques	48

5.2.1	Verification Techniques	48

5.2.2	Validation Techniques	49

5.3	Verification and Validation Tools	49

5.4	Verification and Validation Schedule	50

5.5	Sample Test Cases	50

5.5.1	Functional Testing	50

5.5.2	Usability Testing	52

5.5.3	User Acceptance Testing (UAT)	52

5.5.4	Security Validation	53

6	Software Development Environment	54

7	Discussions	59

7.1	Limitations and Constraints	59

7.2	Health and Safety Issues	59

7.3	Legal Issues	59

7.4	Economic Issues and Constraints	59

7.5	Sustainability	59

7.6	Ethical Issues	59

7.7	Multidisciplinary Collaboration	59

8	References	60

List of Tables

Table 1. Work Packages and Dependencies for CULTURATI CMS	3

Table 2. Use Case Complexity and Description	25

Table 3. Environmental Complexity Factor Calculation	31

Table 4. Technical Factor Value Calculation	32

Table 5. User Story and Story Point Estimation	36

Table 6. Project Verification and Validation details	50

Table 7. Software development environment details	54

List of Figures

Page Number

Figure 1. Cash Flow Diagram	23

Figure 2. Use Case Diagram	25

Abbreviations

| CMS | Content Management System |
| --- | --- |
| EER | Enhanced Entity-Relationship |
| EF | Environment Factor |
| NPV | Net Present Value |
| PHM | Person Hour Multiplier |
| SPMP | Software Project Management Plan |
| SRS | Software Requirement Specification |
| TCF | Technical Complexity Factor |
| UML | Unified Modeling Language |
| WBS | Work Breakdown Structure |

# Scope

The Software Project Management Plan (SPMP) document provides a detailed and structured approach for the CULTURATI project, ensuring the successful development of a robust Content Management System (CMS) and supporting components. This document focuses on managing project planning, execution, monitoring, and delivery for the CULTURATI CMS as well as the simplified visitor-facing application prototypes for testing.

The SPMP encompasses all project activities outlined in the Work Breakdown Structure (WBS), covering tasks such as project scope definition, requirements elicitation, architecture and system design, development, testing, validation, and deployment. It also details resource allocation, cost estimations, project schedules, and effort estimations based on decomposition techniques, use case analysis, and story point methods.

Key components of the SPMP include:

- Project Scope: Defines all project deliverables, exclusions, and objectives to align with stakeholder expectations.

- Project Scheduling and Dependencies: The WBS organizes the tasks into clear milestones, dependencies, and deliverables, ensuring systematic execution of the project.

- Effort Estimation and Resource Planning: The SPMP employs multiple estimation techniques and calculates resource needs, costs, and timelines.

- Monitoring and Measuring: Defines the metrics and tools for tracking project progress, quality, and risks.

- Verification and Validation (V&V): Specifies testing techniques, tools, and schedules to ensure the system meets both functional and non-functional requirements.

- Risk Management: Identifies key risks, mitigation strategies, and external dependencies to minimize project disruptions.

The SPMP focuses on the entire product scope, including functional requirements such as content creation, user and institution management, content approval, and API development for visitor-facing applications. Non-functional requirements (e.g., performance, usability, and security) are also addressed to ensure scalability, compliance, and reliability.

The scope explicitly excludes the development of a fully functional visitor application and advanced features like real-time IoT integration, as these fall outside the team’s current responsibilities. By documenting all activities—completed, ongoing, and intentionally excluded—the SPMP serves as a guiding blueprint, ensuring clarity, accountability, and the successful delivery of the CULTURATI CMS within the defined timeline.

# Project Schedule

## Work Packages & Dependencies

This subsection provides a comprehensive overview of the work packages essential for meeting the project's milestones. It includes a detailed breakdown of tasks, their dependencies, and the team members assigned to each task. A Work Breakdown Structure (WBS) visually represents the hierarchical relationships among tasks, while dependency tables outline interdependencies and sequencing.

Table 1. Work Packages and Dependencies for CULTURATI CMS

| WB | Description | Team Member Responsible | Prerequisite | Total Effort (person hour) |
| --- | --- | --- | --- | --- |
| Deliverable-01 | Initial Plan Document version 1 | Ayesha, Göktuğ, Talal, Tarık, Enes |  |  |
| WP-1.1 | Meeting with Project Supervisor: Held a detailed discussion with the project supervisor regarding the project requirements, scope, and user needs before drafting the document. | Ayesha, Göktuğ, Talal, Tarık, Enes |  | 3 |
| WP-1.2 | Internal Team Meetings | Ayesha, Göktuğ, Talal, Tarık, Enes |  |  |
| WP-1.2.1 | Initial Team Discussion: Conducted a team meeting on Zoom to discuss the project as a whole, delegate responsibilities, and plan document structure. | Ayesha, Göktuğ, Talal, Tarık, Enes | WP-1.1 | 2 |
| WP-1.2.2 | Requirements and Scope Review: Held a second team meeting to review and align on functional and non-functional requirements, as well as the project scope. | Ayesha, Göktuğ, Talal, Tarık, Enes | WP-1.2.1 | 3 |
| WP-1.2.3 | Document Finalization: Met as a team to review the document, finalize details, and ensure readiness for submission. | Ayesha, Göktuğ, Talal, Tarık, Enes | WP-1.2.2 | 3 |
| WP-1.3 | Executive Summary: A brief overview of the project, outlining its purpose and scope, aimed at both CTIS-related individuals and the general public. | Göktuğ | WP-1.2.3 | 3 |
| WP-1.4 | Product Purpose: Defined the reason for developing the product, its objectives, and how it differentiates from competitors. | Ayesha, Göktuğ, Talal, Tarık, Enes | WP-1.1 | 3 |
| WP-1.5 | Product Requirements: Outlined the critical functional and non-functional requirements, including a context diagram for better understanding. | Ayesha, Göktuğ, Talal, Tarık, Enes | WP-1.1 WP-1.2.1 | 3 |
| WP-1.6 | Project Scope: Established the project’s goals, major activities, and WBS, highlighting included and excluded items from the scope. | Göktuğ | WP-1.1 WP-1.2.1 | 5 |
| WP-1.6.1 | Milestones and Deliverables: Listed work products, their delivery dates, and a GANTT chart for project timelines | Göktuğ | WP-1.1 WP-1.2.1 WP-1.6 | 5 |
| WP-1.7 | Software Development Process Model: Described the selected Scrum model, with modifications for the project, and included team members' experience with it. | Ayesha, Tarık | WP-1.2.1 | 5 |
| WP-1.8 | Project Stakeholders and Organization: Identified stakeholders, their roles, responsibilities, and formal reporting relationships | Ayesha, Talal | WP-1.2.1 | 4 |
| WP-1.9 | Project Communication: Defined communication mechanisms, channels, and events, including stakeholder meetings and documentation. | Talal | WP-1.2.1 | 4 |
| WP-1.10 | Project Change Control: Outlined the process for managing and communicating project changes effectively. | Ayesha | WP-1.2.1 | 5 |
| WP-1.11 | Assumptions: Listed assumptions and external dependencies critical for project success. | Göktuğ | WP-1.2.1 | 4 |
| 2WP-1.12 | Risks: Highlighted initial risks, their probability, impact, and risk mitigation strategies | Enes | WP-1.2.1 | 3 |
| Milestone-01 | Initial Plan Document Feedback | Ayesha, Göktuğ, Talal, Tarık, Enes | Deliverable-01 | 1 |
| WP-1.13 | Update Executive Summary | Göktuğ | WP-1.3 | 2 |
| WP-1.14 | Update Non-Functional Requirements | Göktuğ | WP-1.5 | 3 |
| WP-1.15 | Update Functional Requirements | Ayesha, Göktuğ | WP-1.5 | 3 |
| WP-1.16 | Update Project Scope | Ayesha | WP-1.6 | 2 |
| WP-1.17 | Update Project Communication | Talal | WP-1.9 | 3 |
| WP-1.18 | Update Project Change Control | Tarık | WP-1.10 | 3 |
| Deliverable-1.1 | Initial Plan Final Version | Ayesha, Göktuğ, Talal, Tarık, Enes | Deliverable-01 |  |
| Deliverable-02 | SRS version 1 | Ayesha, Göktuğ, Talal, Tarık, Enes | Deliverable-1.1 |  |
| WP-2.1 | Stakeholder Discussions: Conduct meetings and incorporate feedback from Neşe Şahin Özçelik and Umut Hüseyinoğlu. | Ayesha, Göktuğ, Talal, Tarık, Enes | Deliverable-1.1 | 2 |
| WP-2.2 | Define Scope: Establish project boundaries, objectives, and exclusions. | Ayesha | WP-2.1 | 3 |
| WP-2.3 | Product Perspective: Document CMS role within the CULTURATI platform and compare it with existing systems. | Ayesha | WP-2.1 | 3 |
| WP-2.4 | User Characteristics: Define user roles (Content Creators, Editors, and Administrators) and their expectations. | Tarık | WP-2.1 Deliverable-01 | 2 |
| WP-2.5 | Assumptions and Dependencies: Specify key assumptions (e.g., GDPR compliance) and dependencies (e.g., APIs). | Tarık | WP-2.1 | 3 |
| WP-2.6 | Functional Requirements: Define 11 functional requirements (FR-01 to FR-11) with detailed descriptions. | Ayesha | WP-2.1 Deliverable-1.1 | 11 |
| WP-2.7 | Non-Functional Requirements: Document system attributes like usability, performance, and reliability. | Göktuğ, Ayesha | Deliverable-1.1 WP-2.1 | 5 |
| WP-2.8 | System Modeling: Create UML diagrams (Use Case, Sequence, Activity) and EER Diagram for the CMS. | Enes Memigüven, Tarık Ebubekir Koca | WB2.6 | 2 |
| WP-2.9 | Logical Database Requirements: Design database schema, including tables for users, content, and categories. | Talal | Deliverable-1.1 | 12 |
| WP-2.10 | Requirements Prototypes: Develop interactive prototypes for Create Content and Manage Content use cases. | Göktuğ | Functional Requirements (WB2.6) System Modeling (WB2.8) | 11 |
| WP-2.11 | Verification: Define testing strategies for functional and non-functional requirements. | Talal | Functional and Non-Functional Requirements (WB2.6, WB2.7) | 4 |
| Milestone- 02 | Feedback Meeting for SRS | Ayesha, Göktuğ, Talal, Tarık, Enes | Deliverable-02 | 1 |
| WP-2.12 | Review and Refinement: Refine SRS FR1 based on feedback and finalize SRS FR2 for submission. | Ayesha, Göktuğ, Talal, Tarık, Enes | Milestone- 02 | 11 |
| Deliverable 2.2 | SRS Final Version | Ayesha, Göktuğ, Talal, Tarık, Enes | WP-2.12 |  |
| Deliverable-03 | Software Project Management Plan (SPMP) version 1 | Ayesha, Göktuğ, Talal, Tarık, Enes | Deliverable 2.2 |  |
| WP-3.1 | Scope: Write the project scope, defining SPMP activities and exclusions. | Ayesha, Göktuğ | Deliverable-03 | 4 |
| WP-3.2 | Project Schedule | Ayesha, Göktuğ | WP-1.6 |  |
| WP-3.2.1 | Work Packages & Dependencies: Create the WBS, identify dependencies, and assign tasks for all milestones | Ayesha, Göktuğ | WP-1.6 | 12 |
| WP-3.2.2 | Resource Requirements: Estimate resources like personnel, hardware, and software over time. | Tarık |  | 4 |
| WP-3.2.3 | Cost Estimation, NPV, Budget & Resource Allocation: Develop a cash flow diagram, perform NPV analysis, and discuss cost impacts. | Tarık | WP-3.2.2 | 7 |
| WP-3.3 | Project Effort Estimation | Ayesha, Göktuğ |  |  |
| WP-3.3.1 | WBS-Based Estimation | Ayesha | WP-3.2.1 | 4 |
| WP-3.3.2 | Use Case Based Estimation | Göktuğ | WP-2.6 | 6 |
| WP-3.3.3 | Agile Estimation | Ayesha | WP-2.6 | 5 |
| WP-3.3.4 | Discussion: Compare effort estimates and identify the most realistic method. | Ayesha | WP-3.3 | 2 |
| WP-3.4 | Project Monitoring and Measuring: Define monitoring methods and metrics to track project progress. | Enes | WP-3.3 | 3 |
| WP-3.5 | Product Verification and Validation: Plan and execute verification and validation activities, including techniques, tools, schedules, and sample test cases to ensure product quality | Talal | WP-2.11 | 5 |
| WP-3.6 | Software Development Environment: List tools, technologies, and their versions used for development. | Talal | WP-2.3 | 5 |
| WP-3.7 | Discussions: Discuss limitations, constraints, issues (health, legal, economic), sustainability, ethics, and multidisciplinary collaboration encountered during SPMP preparation. | Ayesha, Göktuğ, Talal, Tarık, Enes | Deliverable-03 | 1 |
| Milestone-03 | Feedback Meeting for SPMP | Ayesha, Göktuğ, Talal, Tarık, Enes | Deliverable-03 | 1 |
| WP-3.8 | Review and change SPMP document according to feedback. | Ayesha, Göktuğ, Talal, Tarık, Enes | Milestone-03 | 6 |
| Deliverable-3.1 | Software Project Management Plan (SPMP) final version | Ayesha, Göktuğ, Talal, Tarık, Enes | Milestone-03 Deliverable-03 |  |
| Deliverable-04 | Software Design Description Document (SDD) version 1 | Ayesha, Göktuğ, Talal, Tarık, Enes | Deliverable-03 |  |
| WP-4 | Produce SDD document | Ayesha, Göktuğ, Talal, Tarık, Enes | Deliverable-04 template |  |
| WP-4.1 | SDD Scope | Ayesha | WP-4 | 2 |
| WP-4.4 | SDD Analysis Model & Planning | Ayesha | WP-2.6 WP-2.7 WP-2.8 | 4 |
| WP-4.5 | High-Level (Architecture) Design | Ayesha, Göktuğ, Talal, Tarık, Enes | WP-2.6 WP-2.7 WP-2.8 WP-2.9 | 7 |
| WP-4.6 | Low Level Design | Ayesha, Göktuğ, Talal, Tarık, Enes | WP-4.5 | 11 |
| Milestone-04 | 1st Increment of CULTURATI CMS | Ayesha, Göktuğ, Talal, Tarık, Enes | Deliverable-01, Deliverable-02, Deliverable-03, Deliverable-04 |  |
| WP-5 | Develop 20% of the product | Ayesha, Göktuğ, Talal, Tarık, Enes | Deliverable-01, Deliverable-02, Deliverable-03, Deliverable-04 |  |
| WP-5.1 | Admin Dashboard Development: Develop the admin dashboard interface for managing user accounts and institutions. | Ayesha, Tarık | Deliverable-01, Deliverable-02, Deliverable-03, Deliverable-04 | 15 |
| WP-5.2 | Backend Development: Build backend functionalities to support the admin dashboard and database operations | Talal, Enes, Göktuğ | Deliverable-01, Deliverable-02, Deliverable-03, Deliverable-04 | 17 |
| WP-5.3 | Database Design and Implementation for admin user. | Talal, Enes, Göktuğ | Deliverable-01, Deliverable-02, Deliverable-03, Deliverable-04 | 16 |
| WP-5.4 | Integration of Admin Dashboard with Backend | Ayesha, Göktuğ, Talal, Tarık, Enes | WP-5.1 WP-5.2 | 8 |
| WP-5.5 | Backend-Database Integration: Ensure seamless integration between backend and database to handle CRUD operations | Talal, Enes, Göktuğ | WP-5.2 WP-5.3 | 9 |
| WP-5.6 | Testing of Admin Dashboard: Conduct testing of the admin dashboard for usability, functionality, and responsiveness | Ayesha, Tarık | WP-5.1 | 7 |
| WP-5.7 | Backend Testing: Perform testing to validate backend API performance, security, and functionality. | Talal, Enes, Göktuğ | WP-5.2 | 7 |
| WP-5.8 | Database Testing: Test the database for data integrity, consistency, and query performance. | Talal, Enes, Göktuğ | WP-5.3 | 7 |
| WP-5.9 | Final Integration Testing: Perform end-to-end testing to ensure all components—admin dashboard, backend, and database—are functioning together as expected. | Ayesha, Göktuğ, Talal, Tarık, Enes | WP-5.6 WP-5.7 WP-5.8 | 9 |
| Milestone-05 | 1st Increment Product Presentation | Ayesha, Göktuğ, Talal, Tarık, Enes | WP-5 | 1 |
| WP-5.10 | Meeting with Project Supervisor to discuss 1st increment | Ayesha, Göktuğ, Talal, Tarık, Enes | WP-5 | 2 |
| WP-5.11 | Meeting within the team members to discuss 1st increment and plan 2nd increment. | Ayesha, Göktuğ, Talal, Tarık, Enes | WP-5 | 4 |
| Milestone -06 | 2nd Increment of CULTURATI CMS | Ayesha, Göktuğ, Talal, Tarık, Enes | WP-5 |  |
| WP-6 | Develop 40% of the product focusing on data entry operator and content creator use cases. | Ayesha, Göktuğ, Talal, Tarık, Enes | WP-5 Deliverable-02, Deliverable-03, Deliverable-04 |  |
| WP-6.1 | Data Entry Operator Dashboard Development: Create an interface for data entry operators | Ayesha, Tarık | WP-5 Deliverable-02, Deliverable-03, Deliverable-04 | 14 |
| WP-6.2 | Backend Development for Data Entry Operators: Implement backend functionalities to handle CRUD operations for institutional data. | Göktuğ, Talal, Enes | WP-5 Deliverable-02, Deliverable-03, Deliverable-04 | 15 |
| WP-6.3 | Content Creator Dashboard Development: Design the content creator interface to create, categorize, and manage game and route content. | Ayesha, Tarık | WP-5 Deliverable-02, Deliverable-03, Deliverable-04 | 16 |
| WP-6.4 | Backend Development for Content Creators: Develop backend features for managing content attributes, multimedia uploads, and database integration. | Göktuğ, Talal, Enes | WP-5 Deliverable-02, Deliverable-03, Deliverable-04 | 17 |
| WP-6.5 | Database Design and Implementation for Data Entry Operator and Content Creator Use Cases: Extend the database schema to support these new functionalities. | Göktuğ, Talal, Enes | WP-5 Deliverable-02, Deliverable-03, Deliverable-04 | 13 |
| WP-6.6 | Integration Testing for Data Entry Operator and Content Creator Features: Ensure seamless interaction between dashboards, backend, and database. | Göktuğ, Talal, Enes | WP-5 Deliverable-02, Deliverable-03, Deliverable-04 | 11 |
| WP-6.7 | Testing for Data Entry Operator and Content Creator Features: Validate usability, performance, and accuracy of developed features. | Göktuğ, Talal, Enes | WP-6.1 WP-6.2 WP-6.3 WP-6.5 | 8 |
| Milestone-07 | 2nd Increment Product Presentation | Ayesha, Göktuğ, Talal, Tarık, Enes | Milestone -06 | 1 |
| Milestone-08 | 3rd Increment of CULTURATI CMS | Ayesha, Göktuğ, Talal, Tarık, Enes | Milestone -06, Deliverable-01, Deliverable-02, Deliverable-03, Deliverable-04 |  |
| WP-07 | Develop 40% of the product focusing on editor functionalities, remaining use cases, and final CMS readiness. | Ayesha, Göktuğ, Talal, Tarık, Enes | WP-06 Deliverable-02, Deliverable-03, Deliverable-04 |  |
| WP-7.1 | Editor Dashboard Development: Design an interface for editors to review, approve, or reject content created by content creators. | Ayesha, Tarık | WP-06 Deliverable-02, Deliverable-03, Deliverable-04 | 13 |
| WP-7.2 | Backend Development for Editor Use Cases: Implement features for content approval workflows, notifications, and status updates. | Göktuğ, Talal, Enes | WP-06 Deliverable-02, Deliverable-03, Deliverable-04 | 14 |
| WP-7.3 | Theme and Language Support: Add features to allow users to customize themes (light, dark, or custom) and switch between English and Turkish languages. | Ayesha, Tarık | WP-06 Deliverable-02, Deliverable-03, Deliverable-04 | 9 |
| WP-7.4 | Basic Visitor Applications for Testing: Develop simplified Android and iOS applications to verify that the CMS functions as intended for the visitor-side application. | Ayesha, Tarık | Deliverable-02, Deliverable-03, Deliverable-04 | 12 |
| WP-7.5 | Final Integration Testing: Conduct thorough end-to-end testing to ensure all components, including admin, data entry operator, content creator, editor features, and visitor apps, work together seamlessly. | Göktuğ, Talal, Enes | WP-05 WP-06 Deliverable-02, Deliverable-03, Deliverable-04 WP-7.1 WP-7.2 WP-7.3 WP-7.4 | 18 |
| WP-7.6 | System Optimization and Bug Fixes: Resolve any performance issues or defects identified during testing to ensure a stable release. | Ayesha, Göktuğ, Talal, Tarık, Enes | WP-7.5 | 10 |
| Milestone-09 | Final Product Presentation | Ayesha, Göktuğ, Talal, Tarık, Enes | Milestone-08 | 2 |

## Resource Requirements

#### 1. Personnel

Team Composition:

5 team members: one Project Manager, three Backend Developers, and two Frontend Developers.

Effort Allocation:

Based on Effort Estimation (from WP tasks): ~508 person-hours.

Based on Use Case Estimation: ~3020 person-hours

Based on Story Point Estimation: ~588 person-hours

2. Computer Time

Development:

Average 12 hours per week per developer working on the project.

Approximately 288 hours of computer time per developer for the project duration.

Cost: 0 cost for computer usage

#### 3. Support Software

Primary Tools:

GitHub (repository): Free for educational use.

Jira (task management): Free for up to 10 members

Design Tools (Figma): Free for educational use.

Testing Tools (Postman, JMeter): Free versions used.

ChatGPT premium: 2 people use premium for total of 40$.

Cost:

240$ total for ChatGPT

4. Computer Hardware

Minimum Specifications:

Laptop/Desktop: Intel i5, 8GB RAM, 256GB SSD.

Internet Speed: Minimum 20 Mbps for remote collaboration.

Existing Hardware:

Assume team members have personal laptops meeting the specifications.

Cost of Repair in Malfunctions:

Depends on the type of damage for most common scenario:

Broken Fan: 1000 TL per new Fan including repair cost.

Cost:

1000TL in repair fees in case of malfunctions (e.g. broken fan)

#### 5. Office and Laboratory Facilities

University Resources:

Workspace and internet provided by Bilkent University.

Cost:

0 cost for facilities.

#### 6. Travel and Meeting Costs

Stakeholder Meetings:

Average 2 meetings/month.

Travel (1 car, 1 bus): 110 TL/meeting x 2 meetings/month x 6 months = 1320TL

Coffee for Meetings:

~800 TL/month x 6 months = 4,800 TL.

Total Costs: ~6120TL

#### 7. Maintenance Requirements

Post-Development:

Maintenance ends with project handoff (June 2025).

Resources:

Final documentation and bug fixes.

Cost: 0 cost for maintenance

Generally, the project incurs minimal monetary costs, most of the costs coming from ChatGPT premium membership and travel expenses, and there could be extra costs depending on computer malfunctions. Aside from the monetary cost there is also effort cost calculated as part time effort of 12 hours per week for each developer. Again, there is no monetary personnel cost since the developers are not being paid.

## Cost Estimation, Net Present Value, Budget and Resource Allocation

The project involves recurring expenses associated with regular meetings and software subscriptions. Over the span of project, the expenses are as follows:

- Meeting Costs: Each month, we have held two meetings on average. Two members travel to attend the meetings:

  - One member incurs a car travel cost of 80 TL per meeting.

  - The other incurs a bus travel cost of 30 TL per meeting.

  - On average, 400 TL is spent on coffee for each meeting.

For two meetings per month, the total monthly cost of meetings amounts to: 1020TL on average.

- ChatGPT Premium Subscription:

Two of the group members uses ChatGPT Premium at a cost of 40 USD per month  In total.

- Time Period:

In the span of the project from September 2024 to June 2025, we are expecting same expenditures on average every month.

Figure 1. Cash Flow Diagram

The NPV calculations provide valuable insights into managing our project's finances. TL expenses, with a higher interest rate of 5%, are more costly over time. Paying these costs earlier can help reduce the financial burden. In contrast, USD expenses, with a very low interest rate of 0.1%, remain stable, and their timing has minimal impact on the total cost.

The total adjusted costs for the project, considering the time value of money, are 10.160 TL and 360.00 USD. These values help us understand the true cost of the project and guide us in allocating our resources wisely. Focusing on early payment of TL costs will help manage the budget more effectively and avoid unnecessary financial strain.

This analysis provides clarity for planning and ensures the project’s resources are used efficiently, supporting its overall success.

# Project Effort Estimation

## Work Breakdown Structure (WBS) - Decomposition-Based Estimation

The effort elements for the decomposition-based estimation in Work Breakdown Structure (WBS) are detailed in the Total Effort (person hour) column of table 1, provided in section 2.1. Each work package is broken down into activities that can be assigned and completed by team members and given corresponding effort values. The sum of these values, effort in person hour, can give an effort estimation for the entire project.

The total effort estimated based on the WBS is: 506 person-hour

## Use Case Based Estimation

For use case-based estimation we categorized complexity this way:

- Simple Use Case: 1-3 transactions.

- Average Use Case: 4-7 transactions.

- Complex Use Case: 7+ transactions.

Classifying the Actors:

- Simple Actor (Weight = 1): Another system with a simple interface or a simple protocol.

- Average Actor (Weight = 2): An actor interacting through a standard, well-defined API or a text-based interface.

- Complex Actor (Weight = 3): An actor interacting through a graphical user interface (GUI).

Figure 2. Use Case Diagram

Table 2. Use Case Complexity and Description

| Use Case ID | Description | Classification | Rationale |
| --- | --- | --- | --- |
| UC-01 | Authenticate User | Simple | Single login process with username, password, and captcha validation. |
| UC-02 | Manage Institution | Complex | Includes creating, editing, deleting institutions, assigning users, and viewing details. |
| UC-03 | Create Institution | Average | Involves form inputs for institution creation and basic validations. |
| UC-04 | Manage User Account | Complex | Includes creating, editing, deleting user accounts and assigning roles. |
| UC-05 | Create New User Account. | Average | Requires detailed input form and validation. |
| UC-06 | Manage Category/Difficulty Level/Type | Complex | Involves creating, editing, and deleting categories, difficulty levels, and content types. |
| UC-07 | Create Content | Complex | Involves multiple steps: setting attributes, adding media, previewing content, etc. |
| UC-08 | Preview Content | Simple | Straightforward viewing of how the created content will appear. |
| UC-09 | Manage Content | Complex | Editing, deleting, exporting, and publishing content. |
| UC-10 | Edit User Account Information | Simple | Basic editing of user details like email or name. |
| UC-11 | Change Dashboard Theme | Simple | Straightforward selection of a dashboard theme. |
| UC-12 | Change System Language | Simple | Involves toggling between predefined languages. |
| UC-13 | Create New Category/Difficulty Level/Type | Average | Includes creating and validating fields for categories, difficulty levels, or content types. |
| UC-14 | View All Content | Simple | Simple view operation with filtering. |
| UC-15 | Manage Content for Publishing | Average | Includes approving, rejecting, and updating statuses of content.. |
| UC-16 | Add Institution Details | Average | Involves adding institutional details like name, type, and logo. |
| UC-17 | Edit Institution Details | Average | Editing fields like name, type, and logo. |
| UC-18 | Delete Institution Details | Average | Includes validating and deleting institutions. |
| UC-19 | Access Visitor-Specific Content via API | Complex | Involves API interaction for fetching personalized content. |
| UC-20 | Filter Content by Category, Difficulty, and Type | Average | Filtering operations to refine content searches. |
| UC-21 | View Institution Details | Simple | Simple operation for viewing institutional details. |
| UC-22 | Set up password for first time login | Simple | Simple process for setting a new password. |

Each of the user roles (Admin, Content Creator, Editor, and Data Entry Operator) uses a graphical user interface to interact with the system. The Visitor Application, being an external application consuming APIs, is considered at least average complexity, depending on the type of interaction.

Actors:

- Admin: Uses GUI → Complex = 3

- Content Creator: Uses GUI → Complex = 3

- Editor: Uses GUI → Complex = 3

- Data Entry Operator: Uses GUI → Complex = 3

- Visitor Application: Interacts via API with the system. Average complexity = 2

Unadjusted Actor Weight (UAW):

UAW = Admin (3) + Content Creator (3) + Editor (3) + Data Entry Operator (3) + Visitor Application (2)

UAW = 3 + 3 + 3 + 3 + 2 = 14

Count Each Category of Use Cases:

- Simple Use Cases (5 points): UC-01, UC-08, UC-10, UC-11, UC-12, UC-14, UC-21, UC-22

- Count = 8 simple UCs → 8 × 5 = 40

- Average Use Cases (10 points): UC-03, UC-05, UC-13, UC-15, UC-16, UC-17, UC-18, UC-20

Count = 8 average UCs → 8 × 10 = 80

- Complex Use Cases (15 points): UC-02, UC-04, UC-06, UC-07, UC-09, UC-19

Count = 6 complex UCs → 6 × 15 = 90

Unadjusted Use Case Weight (UUCW):

UUCW = 40 (Simple) + 80 (Average) + 90 (Complex) = 210

Unadjusted Use Case Points (UUCP):

UUCP = UUCW + UAW

= 210 + 14

= 224

Final Use Case Points (UCP):

We need to calculate Environmental and Technical Complexity Factors

Table 3. Environmental Complexity Factor Calculation

| Factor | Description | Value | Notes |
| --- | --- | --- | --- |
| E1 | Familiarity with development process | 3 | Familiar with agile and iterative |
| E2 | Application experience | 2 | Limited CMS experience |
| E3 | OOP experience | 3 | Moderate OOP exposure |
| E4 | Lead analyst capability | 3 | Moderate Lead Capability |
| E5 | Motivation | 4 | High motivation |
| E6 | Stable requirements | 3 | Moderately stable requirements |
| E7 | Part-time staff availability | 2 | Limited hours per week |
| E8 | Programming language/tools experience | 3 | Familiar but not extensive experience |

Table 4. Technical Factor Value Calculation

| Factor | Description | Value | Notes |
| --- | --- | --- | --- |
| T1 | Distributed system | 3 | AWS hosted, moderate complexity |
| T2 | Performance requirements | 2 | ~100 concurrent users manageable |
| T3 | End-user efficiency | 3 | Must be user-friendly |
| T4 | Complex internal processing | 4 | Multiple workflows, approvals, validations |
| T5 | Reusability | 3 | Modular design for component reuse |
| T6 | Easy to install | 1 | Web-based, minimal installation needed |
| T7 | Easy to use | 3 | Emphasis on usability. |
| T8 | Portability | 2 | Works across major browsers |
| T9 | System maintainability | 4 | Priority on maintainability |
| T10 | Concurrent/parallel processing | 2 | Limited parallel operations |
| T11 | Security features | 4 | Role-based access, encryption |
| T12 | Access for third parties via API | 3 | APIs for visitor apps. |
| T13 | Training needs | 1 | Minimal training required |

Sum the Technical Factors (ΣT):

ΣT=35

TCF Formula:

TCF=0.6+(0.01×ΣT)

TCF=0.6+(0.01×35) =0.6+0.35=0.95

TCF = 0.95

Sum the Environmental Factors (ΣE):

ΣE=23

EF Formula:

EF=1.4+(−0.03×ΣE)

EF=1.4+(−0.03×23) =1.4−0.69=0.71

EF = 0.71

Determining the Person-Hours Multiplier (PHM)

- The decision rule is:

If the sum of (# of Efactors E1 through E6 assigned value < 3) AND(# of Efactors E7 and E8 assigned value > 3) =< 2

- PHM = 20

ElseIf: the sum of (# of Efactors E1 through E6 assigned value < 3) AND (# of Efactors E7 and E8 assigned value > 3) = 3 or 4

- PHM = 28

Else

- Rethink project; it has too high of a risk for failure.

Using the decision rule provided:

- Check how many of E1 through E6 are assigned a value < 3.

- Check how many of E7 and E8 are assigned a value > 3.

E1–E6 Values: E1=3, E2=2, E3=3, E4=3, E5=4, E6=3

- E2 is <3. All others are ≥3.

Number of E1–E6 <3 = 1

E7–E8 Values: E7=2, E8=3

- Neither E7 nor E8 is >3 (they are 2 and 3, respectively).

Number of E7–E8 >3 = 0

Sum:

E1–E6<3 = 1

E7–E8>3 = 0

Total = 1+0 = 1

Decision Rule:

- If the sum ≤ 2, PHM = 20

- If the sum = 3 or 4, PHM = 28

- Else, project is too risky.

Here, our sum is 1, which is ≤ 2.

PHM = 20

Calculate the Adjusted Use Case Points (UCP)

UCP=UUCP×TCF×EF

UCP=224×0.95×0.71

UCP≈151

Estimated Person-Hours=UCP×PHM

151×20=3020 person-hours

## Agile Estimation

In this section, we estimate the effort based on user stories and story points. The following points provides user stories, derived from use cases and story points estimated and the justification for each story point assigned to each user story. Story points were assigned using the Fibonacci sequence, based on the complexities estimated by team members.

Table 5. User Story and Story Point Estimation

| Use Case ID | User Story | Story Points | Justification |
| --- | --- | --- | --- |
| UC-01 | As a user, I want to authenticate myself, so that I can securely access the system. | 3 | Basic user authentication requiring backend validation. |
| UC-02 | As an admin, I want to manage institutions, so that I can maintain accurate institution records. | 13 | Includes creating, editing, viewing, and deleting institutions (moderate effort). |
| UC-2.1 | As an admin, I want to create institutions, so that I can add new records | 3 | Input handling and data persistence for institution creation. |
| UC-2.2 | As an admin, I want to edit institution details, so that I can update information. | 3 | Moderate effort for data retrieval and update validation. |
| UC-2.3 | As an admin, I want to delete institutions, so that I can remove outdated records. | 3 | Straightforward deletion with validation. |
| UC-2.4 | As an admin, I want to view institution details, so that I can review and verify data. | 3 | Simple data retrieval and display logic. |
| UC-03 | As an admin, I want to create an institution, so that I can register new institutions. | 2 | Input management and persistence for institution creation. |
| UC-04 | As an admin, I want to manage user accounts, so that I can control user roles and access. | 13 | Includes assigning roles, editing, and deleting user accounts. |
| UC-4.1 | As an admin, I want to create new user accounts, so that I can onboard new users. | 3 | Input validation and user data storage. |
| UC-4.2 | As an admin, I want to edit user accounts, so that I can update user roles or details. | 5 | Moderate complexity for data updates and validations. |
| UC-4.3 | As an admin, I want to delete user accounts, so that I can remove inactive users. | 3 | Deletion logic with safety checks. |
| UC-05 | As an admin, I want to create a new user account, so that I can onboard new users. | 3 | Requires input validation and user data storage. |
| UC-06 | As a content creator, I want to manage categories, so that I can organize content effectively. | 8 | Covers creating, editing, viewing, and deleting categories. |
| UC-6.1 | As a content creator, I want to create new categories, so that I can expand content classification. | 3 | Input handling and validation. |
| UC-6.2 | As a content creator, I want to edit categories, so that I can update classifications. | 3 | Data update and validation logic. |
| UC-6.3 | As a content creator, I want to delete categories, so that I can remove outdated classifications | 2 | Simple delete logic. |
| UC-07 | As a content creator, I want to create content, so that I can provide new material for users. | 5 | Content creation involves input handling and validation. |
| UC-08 | As a content creator, I want to preview my content, so that I can review it before publishing. | 3 | Displaying content for review with simple rendering logic. |
| UC-09 | As a content creator, I want to manage content, so that I can keep it up to date. | 8 | Includes editing and deleting content (moderate effort). |
| UC-9.1 | As a content creator, I want to edit content, so that I can make updates. | 5 | Moderate effort to handle input updates and persistence. |
| UC-9.2 | As a content creator, I want to delete content, so that I can remove outdated material, | 3 | Straightforward deletion process with validation. |
| UC-10 | As a user, I want to edit my account information, so that I can keep my details current. | 3 | Allows user to update their account details. |
| UC-11 | As a user, I want to change the dashboard theme, so that I can personalize my experience. | 2 | Simple UI update with theme persistence. |
| UC-12 | As a user, I want to change the system language, so that I can use the platform in my preferred language. | 3 | Involves localization and moderate complexity |
| UC-13 | As a content creator, I want to create new categories, so that I can expand content classification. | 3 | Creating new categories with validation and input handling |
| UC-14 | As an editor, I want to view all content, so that I can review everything for quality. | 2 | Straightforward retrieval and display of content. |
| UC-15 | As an editor, I want to manage content for publishing, so that I can approve or reject submissions. | 5 | Includes rejecting and approving content for publishing. |
| UC-15.1 | As an editor, I want to approve content, so that it is ready for publishing | 3 | Straightforward status update logic |
| UC-15.2 | As an editor, I want to reject content, so that I can request improvements. | 3 | Validation and rejection handling. |
| UC-16 | As a data entry operator, I want to add institution details, so that I can update system records. | 3 | Input handling and persistence for new institution details. |
| UC-17 | As a data entry operator, I want to edit institution details, so that I can correct any errors. | 3 | Updating institution details with input validations. |
| UC-18 | As a data entry operator, I want to delete institution details, so that I can remove outdated records | 2 | Straightforward deletion with required validation checks. |
| UC-19 | As a visitor application, I want to access specific content via API, so that I can display relevant data to end-users. | 5 | Developing an API for content access involves backend effort. |
| UC-20 | As a visitor, I want to filter content, so that I can find the most relevant material easily. | 5 | Query and filter content based on parameters with logic complexity. |
| UC-21 | As a user, I want to view institution details, so that I can get information about them. | 2 | Simple data retrieval and display for institutions. |
| UC-22 | As a user, I want to set up a password for first-time login, so that I can securely access my account. | 3 | Secure password handling during initial login setup. |

Total Story points = 123

There are 6 user stories with 2 as their story points, let assume on average:

1 story point = 2 person-hour for such user stories, then total effor for such user stories will be

Effort = 2×2×6

For user stories with story point as 3 and 5 which are 26 in total, they will approximately take effort as 1 story point = 3 person-hour.

Effort  = 3×3×20

Effort  = 3×5×6

For user stories with story point as more than 5 which are 4 in total, they will approximately take effort as 1 story point = 7 person-hour.

Effort  = 7×2×8

Effort  = 7×2×13

To calculate the effort in person-hours:

Effort (Person-Hours) = Story Points × Hours per Story Point

Effort = 2×2×6 + 3×3×+ 3×5×6 + 7×8×2 + 7×2×13

Effort in person hour = 588

## Discussion

Work Breakdown Structure (WBS) - Decomposition-Based Estimation

Effort: 506 person-hours

Methodology:

This approach breaks the project into smaller activities or work packages. Each activity is assigned effort estimates, and the total effort is the sum of these individual components.

Strengths:

- Provides detailed effort estimations for each activity.

- Facilitates better project tracking and resource allocation.

Weaknesses:

- Requires detailed task decomposition, which may introduce inaccuracies if certain tasks are overlooked or underestimated.

- Subjective, depending on the team’s experience in estimating effort per task.

Use Case-Based Estimation

Effort: 3020 person-hours

Methodology: This approach calculates the effort based on Use Case Points (UCP). Use cases are classified as Simple, Average, or Complex depending on their transactions. The final effort is adjusted using technical and environmental factors, with a multiplier (PHM) applied to obtain person-hours.

Strengths:

- A structured method that accounts for system complexity and influencing factors (e.g., technical and environmental).

- Suitable for larger systems with well-defined use cases.

Weaknesses:

- Results in significantly higher estimations due to general multipliers and adjustments.

- May overestimate effort if technical/environmental factors are not accurately assessed.

Story Point-Based Estimation

Effort: 588 person-hours

Methodology:

This approach uses story points, where each use case/user story is assigned points based on complexity, and the points are converted to person-hours using an approximation for each user story and its story point based on the complexity.

Strengths:

- Agile and lightweight estimation method that is fast to calculate.

- Allows iterative adjustment based on team performance in real sprints.

Weaknesses:

- Relies heavily on accurate story point assignment, which can be subjective.

- May underestimate effort for larger, complex systems that need more detailed breakdowns.

Differences in the Three Results

The differences in the three results arise due to the level of granularity, assumptions, and methodologies used. WBS focuses on breaking tasks into detailed activities, providing a realistic and tangible estimate (506 hours) that aligns closely with project execution. Use Case-Based Estimation, on the other hand, generalizes effort using technical and environmental factors, leading to a higher estimate (3020 hours) that includes risks and system complexities, often inflating results. Meanwhile, Story Point-Based Estimation simplifies the process by assigning relative points and a conversion for each story point which likely underestimates or overestimates the effort (588 hours) by missing hidden complexities. Overall, WBS appears the most accurate and balanced approach as it offers detailed insights into tasks while avoiding overgeneralization or oversimplification.

Conclusion

Work Breakdown Structure (WBS) appears more realistic for this project because it is based on task decomposition, which aligns closely with how teams execute work. It allows project managers to track effort on a granular level. At 506 person-hours, it provides a balanced and reasonable effort estimate. Also it incorporates all the documentation created for the project.

# Project Monitoring and Measuring

The project meetings will be held weekly Zoom or face to face meetings and can be incremented depending on the needs of the project.

## Monitoring Progress

Progress will be monitored through:

- Weekly Meetings: Weekly face-to-face or Zoom meetings to discuss completed tasks, plan for upcoming work, and address any blockers.

- GitHub for Version Control: Track progress and contributions using GitHub repositories.

- Task Tracker (e.g., Google Sheets): Use a shared spreadsheet to document task assignments, deadlines, and progress status.

- Documentation: Meeting minutes, sprint goals, and updates will be stored in a centralized Google Drive folder for accessibility.

## Metrics

### Project Metrics

Schedule Variance (SV):

- Definition: Measures the difference between planned and actual progress.

- When & How: Weekly, by comparing task completion against planned milestones.

- Storage: Documented in the shared Google Sheets tracker.

Task Completion Rate:

- Definition: Percentage of tasks completed on time in a sprint.

- When & How: Calculated weekly based on task progress.

- Storage: Updated in the Google Sheets tracker.

### Product Metrics

Defect Tracking:

- Definition: Logs and resolves defects identified during development or testing.

- When & How: During testing, record defects in a simple spreadsheet.

- Storage: Stored in the same Google Sheets tracker used for project metrics.

Test Case Pass Rate:

- Definition: Tracks the percentage of test cases successfully passed.

- When & How: Summarized after completing unit and integration tests.

- Storage: Maintained in a shared test case document.

### Process Metrics

Cycle Time:

- Definition: Measures the time taken to complete tasks.

- When & How: Reviewed weekly for significant tasks.

- Storage: Documented in the Google Sheets tracker.

Rework Percentage:

- Definition: Tracks the percentage of tasks requiring rework due to issues.

- When & How: Discussed in weekly meetings and recorded for flagged tasks.

- Storage: Logged in the shared tracker.

## Purpose of Collecting Metrics

- Schedule Tracking: To ensure the project stays on track and delays are addressed early.

- Quality Assurance: To maintain high standards in deliverables by tracking defects and test case results.

- Team Performance: To assess team efficiency through metrics like Task Completion Rate and Rework Percentage.

# Product Verification and Validation

The CULTURATI project aims to create an innovative content management system (CMS) that integrates dynamic, interactive cultural heritage content. This verification and validation (V&V) plan ensure the software is built correctly (verification) and meets the intended objectives and user expectations (validation).

## 5.1 Plan

### Objectives

The V&V process for CULTURATI focuses on:

- Verification: Ensure that key functionalities like user authentication, content creation, and approval workflows meet specified requirements.

- Validation: Confirm that the CMS meets real-world needs, such as providing an intuitive interface and efficient workflows for admins, content creators, editors, and data entry operators.

### Approach

The project follows an iterative development model (Scrum).

- Verification activities, such as code reviews and unit testing, are performed during each sprint.

- Validation is conducted through functional testing, usability testing, and basic user acceptance testing (UAT) at the end of each milestone.

## Verification and Validation Techniques

### Verification Techniques

Code Reviews:

- Peer reviews for source code to ensure correctness and adherence to standards.

- Focus: Login, admin dashboard, and content management functionality.

- Static Analysis:

- Lightweight code quality checks using a linter like ESLint.

- Focus: Code consistency and simple syntax issues.

Unit Testing:

- Individual modules are tested using Vitest or Jest.

- Example: Login process and content submission validation.

Integration Testing:

- Verify the interactions between the frontend, backend, and database.

- Example: CRUD operations for user accounts and institutions.

### Validation Techniques

Functional Testing:

- Validate features like user login, role assignment, and content creation workflows.

Usability Testing:

- Conduct simple user tests to ensure basic functionalities are intuitive.

- Example: Verify that the admin dashboard is user-friendly for assigning roles.

User Acceptance Testing (UAT):

- Gather feedback from project supervisors or classmates to validate core workflows like creating and approving content.

Security Validation:

- Basic checks, such as testing secure login functionality (hashed passwords), without advanced tools like OWASP ZAP.

## Verification and Validation Tools

Code Reviews and Static Analysis:

- Tools: Manual review, ESLint.

- Unit and Integration Testing:

- Tools: Vitest, Jest, Postman for API testing.

Bug Tracking:

- Tools: Google Sheets to log and resolve identified bugs.

## Verification and Validation Schedule

Table 6. Project Verification and Validation details

| Phase | Activity | Tool/Technique | Timeline |
| --- | --- | --- | --- |
| Requirements Analysis | Requirements Review | Manual Verification | September-November 2024 |
| Design Verification | Code Review, Static Analysis | ESLint, Manual Review | November & December 2024 |
| Development Verification | Unit Testing, API Testing | Vitest, Jest | December 2024 & February 2025 |
| Integration Testing | System Interaction Validation | Postman, Manual Testing | March 2025 |
| System Testing | Functional and Usability Testing | Manual Testing | April 2025 |
| User Validation | User Acceptance Testing (UAT) | Feedback from stakeholders | May 2025 |

## Sample Test Cases

### Functional Testing

Test Case ID: TC-FT-001

- Objective: Validate user login functionality.

- Reference: FR-01: User Authentication

- Steps:

- Navigate to the login page.

- Enter valid credentials (username and password).

- Enter the captcha.

- Click "Login."

- Expected Result:

- User is redirected to the dashboard if credentials and captcha are correct.

- An error message appears for incorrect credentials or captcha.

Test Case ID: TC-FT-002

- Objective: Validate role assignment by the admin.

- Reference: UC-04: Manage User Accounts

- Steps:

  - Log in as an admin.

  - Navigate to "User Management."

  - Create a new user and assign the role of "Content Creator."

  - Save the user and verify it appears in the user list.

- Expected Result:

  - The new user is created with the assigned role visible in the user list.

Test Case ID: TC-FT-003

- Objective: Validate content creation workflow.

- Reference: UC-07: Create Content

- Steps:

  - Log in as a content creator.

  - Navigate to the "Create Content" page.

  - Select attributes (category, difficulty level, type) from dropdowns.

  - Enter details for a new game and click "Save."

- Expected Result:

- The content is saved and sent to the editor's review queue.

### Usability Testing

Test Case ID: TC-UT-001

- Objective: Ensure the admin dashboard is user-friendly for role assignment.

- Reference: UC-04: Manage User Accounts

- Steps:

  - Observe a tester with no prior experience navigate the admin dashboard.

  - Ask the tester to create and assign a role to a user.

  - Collect feedback on ease of navigation and clarity of options.

- Expected Result:

  - The tester can complete the task without external guidance.

  - Feedback indicates intuitive navigation.

### User Acceptance Testing (UAT)

Test Case ID: TC-UAT-001

- Objective: Validate the content approval workflow.

- Reference: UC-15: Manage Content for Publishing

- Steps:

  - Simulate a content creator submitting new content.

  - Have an editor review and approve the content.

  - Verify the approved content appears in the CMS API's "published content" endpoint.

- Expected Result:

  - Content approval updates the status to "Published."

  - The approved content is visible via the API for visitor applications.

### Security Validation

Test Case ID: TC-SV-001

- Objective: Verify secure login functionality.

- Reference: NFR: Secure Login

- Steps:

  - Attempt to log in with incorrect passwords three times.

  - Verify account is locked after the third attempt.

  - Check that passwords are hashed in the database.

- Expected Result:

  - Account locks after three failed login attempts.

  - Passwords are stored as hashes and not in plaintext in the database.

# Software Development Environment

Table 7. Software development environment details

| Category | Technology/Tool | Version | Description |
| --- | --- | --- | --- |
| Programming Languages | JavaScript | ES6+ | Used for both frontend and backend development to ensure scalability and flexibility. |
|  | SQL | PostgreSQL-compatible dialect | For managing the relational database schema and queries. |
|  | JSON. | N/A. | Used for API communication between frontend and backend. |
|  | HTML5 & CSS3. | Latest Standards | For building responsive and accessible user interfaces. |
| Frontend Framework | React.js | 18.x (Latest) | Provides a modular and dynamic framework for building the user interface of the CMS and mobile prototype. |
| Backend Framework | Node.js | 23.x (Latest) | Handles server-side logic, RESTful APIs, and interactions with the database.. |
|  | Express.js | 4.x (Latest) | Lightweight framework for routing and middleware in the CMS backend.. |
| APIs & Libraries | Axios | Latest Stable Version | Handles API calls between frontend and backend efficiently. |
|  | Bcrypt | Latest Stable Version | Provides secure password hashing for user authentication. |
|  | AWS SES | Latest Stable Version | Amazon Simple Email Service (SES) handles email functionality, including bulk emails and notifications. |
|  | RESTful API | N/A | Ensures standardized communication between the frontend and backend using JSON over HTTPS. |
|  | JWT | Latest Stable Version. | JSON Web Tokens are used for secure user authentication and session management. |
| Database | PostgreSQL. | Latest Stable Release | Serves as the relational database management system, ensuring data integrity and scalability. |
| Cloud Services | AWS Amplify | Latest | Provides seamless deployment and hosting for web and mobile applications. |
|  | AWS Lambda | Latest | Supports serverless execution of specific tasks and workflows. |
|  | AWS RDS. | PostgreSQL-Compatible | Provides a scalable relational database service for CMS storage and retrieval. |
| Version Management | Git | Latest Stable Version | Used for source control and version management across the development tea |
|  | GitHub | N/A | Hosts the project's code repository, supporting collaboration and CI/CD workflows. |
| Testing Tools | Vitest | Latest Stable Version | Facilitates unit and integration testing for both frontend and backend components.. |
|  | Postman | Latest | Used to test API endpoints during development. |
| Project Management | Google Sheets | Browser Version | Manages Scrum workflows, sprints, and project tracking. |
|  | Zoom | Latest Stable Version | Facilitates team communication and collaboration. |
|  | Gantt Charts | N/A | Used to visualize project milestones and deliverables. |
|  | Slack | N/A | Facilitates urgent team communication and project trackings. |
| Verification & Validation (V&V) | SonarQube | Latest Stable Version | Conducts static analysis to identify code quality issues and security vulnerabilities. |
|  | Jest/Vitest | Latest Stable Version | Used for unit testing frontend and backend modules to ensure functional correctness. |
|  | Postman | Latest Stable Version | Validates API endpoints and integration testing. |
|  | Apache JMeter | Latest Stable Version | Simulates concurrent user traffic to evaluate system performance and scalability. |
|  | OWASP ZAP | Latest Stable Version | Identifies security vulnerabilities and ensures GDPR compliance. |
| Design Tools | Figma. | N/A | Used to create UI/UX prototypes for the CMS and mobile interfaces. |
| Deployment Tools | Vercel | N/A | Deploys the frontend applications with continuous delivery features. |
|  | AWS CLI | Latest Stable Version | Enables management of AWS services for the project's deployment needs. |

# Discussions

## Limitations and Constraints

We had a lot of schedule conflicts since almost all of us are in different sections and have different schedules. This hindered our ability to prepare the SPMP document.

## Health and Safety Issues

No health issues were present when preparing the SPMP document.

## Legal Issues

We didn't have any activities in this document that would cause a legal issue for us.

## Economic Issues and Constraints

There were no Economic issues of immediate concern during the preparation of the SPMP document. There was only beverage and travel expenditures during our meetings.

## Sustainability

We conducted no sustainability related activities during the creation of this document.

## Ethical Issues

There were no ethical issues present during the preparation of SPMP document

## Multidisciplinary Collaboration

Normally we indirectly collaborate with the Stakeholders from THM, specifically Dr. Eda Gürel. But for preparation of this document, we didn't have any multidisciplinary collaboration since this document was mostly about the planning of the project for our team.

# References

| [1] | A. Nizam, T. S. Zafeer, G. Şenkoyun, T. E. Koca ve E. Memigüven, «Software Requirement Specifications,» 024. |
| --- | --- |

GenAI tool: gpt 4.0

Prompt: provide me with an executive summary of exact one page for spmp document that i have already provided. in this summary

GenAI: gpt 4.0

prompt this is the entire product and project, look at the fucntional requirements and everyting , not just admin part, now answer Briefly describe the scope of the project management plan activities and the Software Project Management Plan (SPMP) document with relation to the software product you are developing.

GenAI: gpt 4.4

Prompt: turn this into wbs and also I gave details on what we were supposed to do in each part of initial plan so summarize that paragraphs i have given under each into a sentence or two like description: the main project idea was established etcthis is for the document Software Project Management Plan, SPMP, create the WP using the above information like you did before, start the numbering from WP-3.1 Scope and give a small description

GenAI Tool: chatGPT 4 Prompt: create all the parts required in this text Here is our costs for the project from September to December we made 8 meetings, for meetings 2 of the group members have to travel which one of them with car costing 80tl other one with bus costing 30tl, also on meetings we spend 400tl on coffee on average. (consider each month 2 meeting is done) also every month 2 of the members uses chatGPT premium so they spend 40 dollars every month.

Estimation Decompose your software product & supporting software engineering processes, add them effort elements and add them up. You should reference the WBS given in section 2.1. can i directly add the the effort of column 5 when the person number for every WP is different, how can i calculate total effort from WPS

GenAI Tool: Chatgpt 4o and O1-preview

Prompt: given The instructions and the srs file also the screenshot of the use case diagram with complexities assigned calculate the ucp for this project also i am providing a table with EF and TCF factors so calculate it according to that also.

using all the usecases and also sub use cases create use case narative and user story, i want a list of use case narative and give story point to each use case and a one line justification for the point assigned, calculate Story Point (SP) for each Use Case. to this refer to the following pdf set of guidelines

convert this total story point to effort in person hour

GenAI tool:chatgpt4.1

Prompt: Gave all of the estimations and said Compare and discuss these three different estimations on your effort. Discuss why there are differences between the three estimation results. Discuss which one is more accurate / more realistic.

GenAI Tool: ChatGPT 4o

Prompt: “Based on the technical guide, initial plan, and software requirement specification documents provided create a detailed Product Verification and Validation Plan. I need the plan to outline clear objectives, describe verification techniques (like code reviews and unit testing) and validation techniques (like usability and performance testing), specify the tools to be used, provide a schedule for these activities, and include sample test cases. Ensure the plan aligns with the project's goals and requirements for delivering a robust and user-friendly CMS."

Rationale: To get a better understanding of the applicable types of testing and tools that can be utilized within the scope of our project and provide clear Verification and Validation plan.